## Data
Queue Number | Name | Commercial Name | State | County | Status | Transmission Owner | MFO | MW Energy | MW Capacity | MW In Service | Capacity or Energy | Project Type | Fuel | Project (AC/DC) | Rights (MW) | Initial Study | Feasibility Study | Feasibility Study Status | System Impact Study | System Impact Study Status | Facilities Study | Facilities Study Status | Interim Interconnection Service Agreement | Interim/Interconnection Service Agreement Status | Wholesale Market Participation Agreement | Construction Service Agreement | Construction Service Agreement Status | Upgrade Construction Service Agreement | Upgrade Construction Service Agreement Status | Backfeed Date | Queue Date | Long-Term Firm Service Start Date | Long-Term Firm Service End Date | Test Energy Date | Withdrawal Date | Withdrawn Remarks | Projected In Service Date | Revised In Service Date | Actual In Service Date | Attachment Type | Alternate Queue | Sliding Queue
X4-014 | Kellam - Bayview 69kV |  | VA | Northampton | Withdrawn | ODEC | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4014_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/28/2011 | N/A | N/A |  | 7/3/2012 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
AA1-128 | Glen Lyn |  | VA | Giles | Withdrawn | AEP | 10 | 10 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1128_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1128_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 7/24/2015 | Customer Initiated Withdrawal | 10/1/2016 |  |  | N | No
AA2-129 | New Church 138kV |  | VA | Accomack | Withdrawn | DPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2129_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2129_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 6/8/2018 |  | 12/31/2016 |  |  | N | No
AB1-022 | Columbia 115kV |  | VA | Louisa | Withdrawn | Dominion | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1022_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/6/2015 | N/A | N/A |  | 4/6/2020 |  | 3/31/2017 | 3/31/2017 |  | Y | No
AB2-030 | Tasley 25kV |  | VA | Accomack | Withdrawn | DPL | 4 | 4 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2030_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/11/2016 | N/A | N/A |  | 10/16/2017 |  | 12/1/2016 |  |  | N | No
AC1-206 | Clubhouse 230kV |  | VA | Greensville | Withdrawn | Dominion | 85 | 85 | 57.72 |  | Capacity | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1206_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1206_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 1/18/2018 |  | 10/1/2019 |  |  | N | No
AD1-042 | Stuarts Draft-Waynesboro 115 kV |  | VA | Augusta | Withdrawn | Dominion | 150 | 0 | 12.5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1042_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2017 | N/A | N/A |  | 4/10/2018 |  | 10/31/2018 |  |  | N | No
AD1-050 | Beechwood DP-Palmer Springs 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 45 | 45 | 29.1 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1050_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/7/2017 | N/A | N/A |  | 10/15/2019 |  | 12/1/2019 |  |  | N | No
AD2-049 | Newport News 23kV | Newport News Battery Storage | VA | City of Newport News | Withdrawn | Dominion | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2049_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2049_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad2049_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad2049_wmpa.pdf | Not Required | N/A | N/A |  | 1/31/2018 | N/A | N/A | 4/30/2021 | 10/21/2019 |  | 4/30/2021 | 4/30/2021 |  | N | No
AD2-205 | Byllesby 69 kV | Buck & Byllesby Hydro Project | VA | Carroll | In Service | AEP | 4 | 4 | 0 | 4 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2205_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2205_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad2_205_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/13/2018 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 1/31/2019 | N | No
AE1-010 | Locust Grove-Paytes 115 kV |  | VA | Orange | Withdrawn | Dominion | 95.5 | 33 | 33 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1131_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2018 | N/A | N/A |  | 3/11/2019 |  | 9/30/2021 |  |  | N | No
AE1-135 | Clubhouse 230 kV |  | VA | Greensville | Withdrawn | Dominion | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1135_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 3/19/2019 |  | 6/30/2019 |  |  | N | No
AE1-145 | Wallops Island 69 kV |  | VA | Accomack | Active | ODEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1145_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 12/1/2020 |  |  | N | No
AE1-152 | Gosport 34.5 kV |  | VA | City of Portsmouth | Withdrawn | Dominion | 21.5 | 21.5 | 20.2 |  | Capacity | Generation Interconnection | Natural Gas; Diesel; Other; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 10/16/2018 |  | 10/16/2020 |  |  | N | No
AE1-174 | Light Foot 34.5 kV |  | VA | James City | Withdrawn | Dominion | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1174_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1174_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 9/25/2018 | N/A | N/A |  | 6/16/2020 |  | 10/23/2020 |  |  | N | No
AE1-230 | Shockoe 69 kV |  | VA | Pittsylvania | Active | Dominion | 20 | 20 | 7.2 |  | Capacity | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1230_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1230_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  |  |  | 7/31/2020 |  |  | N | No
AE1-248 | Bell Avenue 115 kV |  | VA | Southampton | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1248_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2018 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No | This project slid to the next queue
AE1-249 | Reams 115 kV |  | VA | Dinwiddie | Withdrawn | Dominion | 70 | 70 | 40.1 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1249_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1249_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  | 1/10/2020 |  | 12/31/2021 |  |  | N | No
AE1-250 | Smith Mountain-E. Danville 138 kV |  | VA | Pittsylvania | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1250_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2018 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AE2-019 | New Road 230 kV |  | VA | Loudoun | Active | Dominion | 120 | 120 | 120 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2019_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2019_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/11/2018 | N/A | N/A |  |  |  | 11/30/2020 |  |  | N | No
AE2-040 | Sapony 34.5 kV |  | VA | Sussex | Active | Dominion | 17.6 | 17.64 | 15.7 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2040_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AE2-041 | Harmony Village 230 kV |  | VA | Middlesex | Active | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2041_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/23/2019 | N/A | N/A |  |  |  | 11/30/2020 |  |  | N | No
AE2-052 | Disputanta-Poe 115 kV |  | VA | Prince George | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2052_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2052_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2019 | N/A | N/A |  |  |  | 9/15/2021 |  |  | N | No
AE2-053 | Kerr Dam-Ridge Road 115 kV |  | VA | Mecklenburg | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2053_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2053_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2019 | N/A | N/A |  |  |  | 9/15/2021 |  |  | N | No
AE2-094 | Carson-Rogers Road 500 kV |  | VA | Sussex | Active | Dominion | 300 | 300 | 207.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2094_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2094_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-150 | Bakers Pond-Bell Ave 115 kV |  | VA | Sussex | Active | Dominion | 75 | 0 | 0 |  | Energy | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2150_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2150_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/14/2019 | N/A | N/A |  | 8/26/2019 |  | 6/1/2022 |  |  | N | No
AE2-156 | Yadkin 115 kV |  | VA | City of Chesapeake | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2156_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2156_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AE2-185 | Gladys DP-Stonemill Switching Station 69 kV |  | VA | Campbell | Active | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2185_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2185_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 9/1/2020 |  |  | N | No
AE2-187 | Shockoe DP-Chatham 69 kV |  | VA | Pittsylvania | Active | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2187_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2187_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 9/1/2020 |  |  | N | No
AE2-188 | Mitchell DP-Mountain Run 115 kV |  | VA | Culpeper | Withdrawn | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2188_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2188_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  | 3/27/2020 |  | 12/31/2020 |  |  | N | No
AE2-260 | Clubhouse 230 kV |  | VA | Greensville | Active | Dominion | 200 | 200 | 82.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2260_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2260_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 6/30/2020 |  |  | N | No
AE2-270 | Hopewell-Surry 230 kV |  | VA | Surry | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2270_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2270_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 9/29/2021 |  |  | N | No
AE2-326 | Jacksons Ferry 138 kV |  | VA | Wythe | Active | AEP | 127.2 | 52.2 | 31.32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2326_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2326_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF1-018 | Harmony Village 230 kV |  | VA | Middlesex | Active | Dominion | 80 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1018_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/3/2019 | N/A | N/A |  |  |  | 11/30/2020 |  |  | N | No
AF1-028 | Endless Caverns 115 kV |  | VA | Rockingham | Active | Dominion | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1028_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/13/2019 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF1-031 | Kings Dominion DP 115 kV |  | VA | Caroline | Active | Dominion | 93.5 | 93.5 | 60.69 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1031_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/17/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-038 | Sewellton Jct-Webbs Crossroads 69 kV |  | VA | Russell | Active | EKPC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1038_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/6/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF1-059 | Brodnax-South Hill 115 kV |  | VA | Mecklenburg | Active | Dominion | 99.2 | 99.2 | 99.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1059_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2019 | N/A | N/A |  |  |  | 10/31/2021 |  |  | N | No
AF1-066 | New Road 230 kV |  | VA | Loudoun | Active | Dominion | 300 | 130 | 130 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1066_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/2/2019 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AF1-067 | Kings Dominion DP 115 kV |  | VA | Caroline | Active | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1067_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/8/2019 | N/A | N/A |  |  |  | 12/16/2022 |  |  | N | No
AF1-069 | Carson-Rogers Rd 500 kV |  | VA | Sussex | Active | Dominion | 394 | 94 | 67.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1069_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/9/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-201 | Hayes-Whitemarsh 115 kV |  | VA | Gloucester | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1201_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF1-231 | New Church 138 kV |  | VA | Accomack | Active | DPL | 19 | 19 | 7.6 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1231_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-243 | Tasley 25 kV |  | VA | Accomack | Active | ODEC | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1243_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 6/30/2020 |  |  | N | No
AF1-265 | Four Rivers-Hanover 230 kV |  | VA | Hanover | Active | Dominion | 450 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1265_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-266 | Clubhouse-Sapony 230 kV |  | VA | Dinwiddie | Active | Dominion | 223.5 | 74.5 | 74.5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1266_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-293 | Kidds Store-Fort Union 115 kV |  | VA | Fluvanna | Active | Dominion | 127.9 | 127.86 | 109.92 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1293_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AF2-013 | Arnold's Corner-Dahlgren 230 kV |  | VA | King George | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/15/2019 | N/A | N/A |  |  |  | 10/1/2023 |  |  | N | No
AF2-040 | Elk Run-Gainesville 230 kV |  | VA | Fauquier | Active | Dominion | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/4/2019 | N/A | N/A |  |  |  | 10/1/2023 |  |  | N | No
AF2-055 | Plantation 69 kV |  | VA | Northampton | Active | ODEC | 50 | 50 | 35 |  | Capacity | Generation Interconnection | Storage; Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/16/2020 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AF2-057 | Grassfield 34.5 kV |  | VA | Mecklenburg | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2020 | N/A | N/A |  |  |  | 4/1/2022 |  |  | N | No
AF2-060 | Wattsville 12 kV |  | VA | Accomack | Active | DPL | 9 | 9 | 9 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2020 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AF2-061 | Wattsville 69kV |  | VA | Accomack | Active | DPL | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2020 | N/A | N/A |  |  |  | 6/30/2021 |  |  | N | No
AF2-085 | Midlothian 34.5 kV |  | VA | Chesterfield | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2020 | N/A | N/A |  |  |  | 6/30/2021 |  |  | N | No
AF2-108 | Locks 34.5 kV |  | VA | Dinwiddie | Active | Dominion | 17.5 | 17.5 | 17.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2020 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AF2-144 | Powhatan 34.5 kV |  | VA | Powhatan | Active | Dominion | 17 | 17 | 10.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2020 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-266 | Clover 230 kV |  | VA | Charlotte | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 7/1/2022 |  |  | N | No
AF2-279 | Letort 12.47 kV |  | VA | Lancaster | Active | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 7/1/2021 |  |  | Y | No
AF2-284 | Watson 12.47 kV |  | VA | Northumberland | Active | PPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 8/1/2021 |  |  | Y | No
AF2-304 | Surry-Hopewell 230 kV |  | VA | Prince George | Active | Dominion | 150 | 150 | 89 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 8/3/2023 |  |  | N | No
AF2-327 | Wakefield 13 kV |  | VA | Sussex | Active | Dominion | 20 | 20 | 16 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 8/3/2023 |  |  | N | No
AF2-397 | Fork Union-Mt. Eagle 230 kV |  | VA | Fluvanna | Active | Dominion | 130 | 130 | 78 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AF2-403 | Shockoe DP-Chatham 69 kV |  | VA | Campbell | Active | Dominion | 60 | 0 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/15/2022 |  |  | N | No
AF2-404 | Gladys DP-Stonemill 69 kV |  | VA | Campbell | Active | Dominion | 60 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/15/2022 |  |  | N | No
AG1-009 | Hopewell-Surry 230kV |  | VA | Surry | Active | Dominion | 150 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/4/2020 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AG1-010 | Ladysmith-CT-St. Johns 230 kV |  | VA | Caroline | Active | Dominion | 180 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/5/2020 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AG1-011 | Colonial Trial 230 kV |  | VA | Surry | Active | Dominion | 160 | 160 | 160 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/8/2020 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AG1-012 | Mewdow Brook-Strasburg 138 kV II |  | VA | Frederick | Active | APS | 75 | 0 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/8/2020 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AG1-013 | Ladysmith CT-St. Johns 230 kV |  | VA | Caroline | Active | Dominion | 120 | 0 |  |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/8/2020 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AG1-014 | Carson-Rogers Rd 500 kV |  | VA | Greensville | Active | Dominion | 500 | 0 |  |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/8/2020 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AG1-015 | Carson-Rogers Rd 500 kV |  | VA | Greensville | Active | Dominion | 400 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/8/2020 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AG1-019 | Arnold's Corner-Dahlgren 230 kV |  | VA | King George | Active | Dominion | 200 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/20/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AG1-020 |  |  | VA | Loudoun | Withdrawn | Dominion |  |  |  |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/20/2020 | N/A | N/A |  | 6/16/2020 |  | 10/31/2023 |  |  | N | No

## Definitions-Mapping
Column Names from Data Tab
Queue | Queue/OASIS Number
Name | The commercial name becomes public after the System Impact Study is issued. Not all developers have a commercial name once the System Impact Study is posted and there is no tariff requirement for them to have one. Also, the name users search under may vary. For ARR upgrades, the project name is the source and sink. Name is also referred to as the following: PJM Substation, Terminals, Customer Name and Source + Sink.
Commercial Name | The commercial name becomes public after the System Impact Study is issued. Not all developers have a commercial name once the System Impact Study is posted and there is no tariff requirement for them to have one. Also, the name users search under may vary. For ARR upgrades, the project name is the source and sink. Name is also referred to as the following: PJM Substation, Terminals, Customer Name and Source + Sink.
State | The state the project resides in.
County | Point of Interconnection County
Status | Contains the following statuses: Active, Active-In Service, Annulled, Cancelled, Confirmed, Engineering Procurement, In Service, Pending, Renewal, Retracted, Suspended, Under Construction, Under Construction - In Service & Withdrawn
Transmission Owner | A member that owns or leases, with rights equivalent to ownership, Transmission Facilities. Taking transmission service is not sufficient to qualify a Member as a Transmission Owner. Path name is included.
MFO | Maximum Facility Output
MW Energy | The MW energy for the interconnection request (winter net).
MW Capacity | The Capacity interconnection request for the queue position (summer net).
MW In Service | The number of megawatts when the project is in service.
Capacity or Energy
Project Type | GI: Generation Interconnection, TI: Transmission Interconnection, LTFT: Long-Term Firm Transmission, UR: Upgrade Request
Fuel | The type of fuel the project is running.
Project (AC/DC) | AC or DC
Rights (MW) | The type of rights the terminal has.
Initial Study
Feasibility Study | A Feasibility Study assesses project practicality and developer cost to interconnect to PJM and is the first study in the interconnection process.
Feasibility Study Status
System Impact Study | A System Impact Study provides a comprehensive and detailed system analysis that tests deliverability under peak load conditions as well as tests impacts on system stability.
System Impact Study Status
Facilities Study | A Facilities Study encompasses the engineering design work necessary to begin construction of required expansion plan upgrades identified by PJM to accommodate an interconnection request.
Facilities Study Status
Interim Interconnection Service Agreement | Under certain circumstances, an applicant for an ISA may wish to initiate project construction activities on an expedited basis prior to completion of the Facilities Study.
Interim Interconnection Service Agreement Status
Wholesale Market Participation Agreement | The WMPA request is placed into the interconnection queue process so that PJM may assess the impact of any such wholesale power transactions on the PJM bulk power system.
Construction Service Agreement | The terms and conditions of a Construction Service Agreement govern the construction of all transmission facilities for interconnection to the PJM transmission system. PJM and the developer execute a separate CSA with each impacted transmission owner. A developer retains the right (“Option to Build”), but not the obligation to design, procure, construct and install all or any portion of required transmission upgrades which are otherwise the obligation of the Transmission Owner to construct.
Construction Service Agreement Status
Upgrade Construction Service Agreement | The terms and conditions of an Upgrade Construction Service Agreement govern the construction activities associated with the upgrade of capability along an existing PJM bulk electric system circuit in order to accommodate a merchant transmission interconnection request. Facilities constructed under an UCSA are not owned by a developer. All ownership rights of the physical facilities are retained by the respective Transmission Owner following the completion of construction. PJM and the developer execute a separate UCSA with each impacted transmission owner.
Upgrade Construction Service Agreement Status
BackFeed Date
Queue Date
LTF Service Start Date
LTF Service End Date
Test Energy Date
Withdrawal Date
Withdrawn Remarks | CIW: Customer Initiated Withdraw, CMN: Customer Milestone Not Met, QNR: Queue Not Required, WBSD: Withdrawn Before Study Due
Revised In Service Date
Actual In Service Date
Date Suspended
Attachment Type | N, Y, BB = Generation Interconnection, S = Transmission Interconnection, EE = Upgrade Request, FF = Transmission Service
Alternate Queue
Sliding Queue